## Summary
DropLine Connect Four - Thorough Harbor Task QC
Rework review using the harbor-task-qc skill, local executable checks, and preserved Harbor run evidence.
Rechecked 2026-08-28. Golden engine, Docker, startup, browser rendering, architecture enforcement, timeout handling, and judge metadata checks passed locally. The Oracle attempt reached RewardKit but could not grade because the supplied OpenRouter key had expired.
Task | Prior | Fixed | Partial | Not fixed | Unknown | New | Introduced by rework | Missed in QC1 | Verdict
DropLine | 3 | 3 | 0 | 0 | 0 | 11 | 2 | 8 | Golden behavior and all identified task-side P1/P2 fixes are clean; a fresh API key is required to obtain the remaining Oracle score of exactly 1.0.
Prior finding closure
3 of 3 prior fixes remain present and pass current local checks.
The verifier-calibration findings DL-N02 through DL-N09 were corrected without changing the required game behavior.
Executed validation
Parsed task.toml and browser.toml: 26 unique binary criteria, browser weight 19.5, preflight weight 0.5, total 20.0.
Ran all 16 Node engine tests locally and in the exact rebuilt Docker image: 16/16 passed both times.
Started the golden in the task image, verified /health and /api/config, and rendered exactly 42 grid cells with the pinned Chromium executable.
Verified Codex CLI 0.150.1, Chromium 152.0.7977.8, and Playwright MCP 0.0.79 in the rebuilt image.
Attempted Harbor Oracle: task preflight passed and judge policy matched, but the supplied OpenRouter key was expired before any criterion could be graded.
Ran headless Chromium at desktop and 375x760; no horizontal overflow and all primary controls were usable.
Ran 11 scripted browser flows covering gravity, full-column rejection, four Red win directions, Yellow win, draw, terminal Undo/Redo/reload, next round/reset, persisted Redo, and keyboard controls.
Verified the no-package failure path writes reward.json, reward.txt, and report.json with reward 0.0.
Clean areas
No embedded credential, host-specific path, database, Python cache, TODO/FIXME marker, or source syntax issue was found inside the Harbor task.
Golden rule math, score reversal, branch invalidation, round starter alternation, and reload idempotency passed executable tests.
The split instruction files and seed asset are coherent and available under /instructions and /assets.

## DropLine
ID | Type | Sev | Status | Origin | Area | What the rework did / what is wrong | Action needed | Owner | Track
DL-P01 | Prior | P0 | FIXED |  | Packaging | The prior unavailable Ubuntu curl revision is now pinned to curl=8.5.0-2ubuntu10.13. | No action. Keep the working pin and revalidate it whenever the image is rebuilt for delivery. |  | Closed
DL-P02 | Prior | P1 | FIXED |  | Verifier-Coverage | The prior Red-only winning-treatment coverage now includes an exact Yellow horizontal win and checks exactly four highlighted Yellow cells. | No action. Preserve the Yellow positive control. |  | Closed
DL-P03 | Prior | P2 | FIXED |  | Verifier-Coverage | The versioned dropline:v1 storage requirement is now inspected and compared with visible state before and after reload. | No action. Behavioral storage validation now accepts equivalent internal representations. |  | Closed
DL-N01 | New | P0 | OPEN | Carry-over of a prior finding | Golden-Solution | The complete Harbor Oracle path reached RewardKit, but grading stopped before criterion 1 because the supplied OpenRouter API key returned HTTP 401 `API key expired`. | Rerun and inspect Oracle with a valid key; do not ship until it returns exactly 1.0. |  | Open
DL-N02 | New | P1 | FIXED | Pre-existing, missed in QC1 | Prompt | The weighted preflight now grades successful first start and restart without requiring APP_MANIFEST.md or private /health and /api/config route documentation. | No action. Keep optional manifest start-command discovery as an ungraded convenience. |  | Closed
DL-N03 | New | P1 | FIXED | Pre-existing, missed in QC1 | Verifier-Strictness | Unrelated criteria now begin in fresh isolated browser storage instead of routing setup through Reset Match. | No action before Oracle. Confirm individual runs start fresh in the Oracle evidence. |  | Closed
DL-N04 | New | P1 | FIXED | Introduced by rework | Verifier-Strictness | The persistence criterion now requires the complete semantic dropline:v1 state while explicitly accepting equivalent property names, nesting, coordinate bases, and Redo representations. | No action. Preserve the behavioral Redo-after-reload proof. |  | Closed
DL-N05 | New | P1 | FIXED | Pre-existing, missed in QC1 | Verifier-Strictness | Both keyboard criteria now inspect the actually focused column control and no longer require the golden solution's selected-column text readout. | No action. Preserve the exact key, boundary, focus, placement, turn, and history checks. |  | Closed
DL-N06 | New | P2 | FIXED | Pre-existing, missed in QC1 | Verifier-Strictness | Accessibility and draw checks now accept semantic equivalent wording, motion checks are behavior-based, and the private 1-second/0.01-second thresholds were removed. | No action. Oracle should confirm the judge can obtain the behavior-based transition evidence. |  | Closed
DL-N07 | New | P1 | FIXED | Introduced by rework | Hygiene | The ignored node_modules directory was moved outside the task root while package-lock.json remains present. | No action. Continue packaging from tracked files and keep node_modules outside the task. |  | Closed
DL-N08 | New | P2 | FIXED | Pre-existing, missed in QC1 | Packaging | The npm ci/npm install subprocess is the only verifier subprocess without a timeout. | No action. Preserve the 900-second install timeout and explicit timeout log. |  | Closed
DL-N09 | New | P2 | FIXED | Pre-existing, missed in QC1 | Verifier-Coverage | The brief's Node.js, Express, plain HTML/CSS/JavaScript, no React/game-framework, and no runtime-CDN contract is now mechanically checked during preflight. | No action. Keep the source/package checks aligned with the stated architecture contract. |  | Closed
DL-N10 | New | P3 | UNKNOWN | Pre-existing, missed in QC1 | Packaging | Executable archive modes cannot be verified because the task is untracked and no delivery ZIP exists. | Verify archive modes at packaging time. |  | Verify at packaging
DL-N11 | New | P3 | OPEN | Pre-existing, missed in QC1 | Verifier-Strictness | RewardKit is serialized to one agent and one LLM, while 26 individual criteria each allow 900 seconds. Their theoretical ceiling exceeds the 13,200-second RewardKit timeout. | Reassess after the first Oracle run; lower per-item timeout or raise the global cap based on evidence. |  | Open