## Summary
PatchPad Editor 1.3 - QC Rework
Closure review against PatchPad_Editor_QC.xlsx
All 13 prior findings were rechecked. Static, local restart, and Docker golden checks completed on 2026-08-25; a fresh Harbor Oracle run remains the final release gate.
Task | Prior | Fixed | Partial | Not fixed | Unknown | New | Introduced by rework | Missed in QC1 | Verdict
PatchPad 1.3 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13 of 13 prior findings are structurally closed; run a fresh Oracle before release to replace the superseded 1.2 proof.
P0/P1 closure
Per-criterion individual judging replaces the compacted 20-check session.
The score is recomputed after an exact-marker evidence gate, so unsupported yes verdicts no longer reach reward.json.
Undo granularity is now stated in the brief, both modifier-click choices are accepted, and probe repair is forbidden.
Golden checks
The environment image builds with /instructions and /assets readable.
The golden solution starts in Docker at revision 1 with one document, one revision, and exactly 1,226 expected lines.
The deterministic preflight passes locally with identical logical SQLite digests across restart.
Release gate
Run a fresh Oracle because the previous 1.0 used the superseded batched judge.
Check that rewardkit-browser/judge-transcripts/index.json lists non-empty JSONL session files.

## Run Evidence
Run evidence
From each trial's result.json, verifier/agentic.json, report.json and screenshots/.
Task | Model / agent | Reward | Prog | Agent s | Verifier s | Note
patchpad-editor | ORACLE (prior 1.2 baseline) | 1 | 1 | 7 | 2509 | Superseded evidence: the prior batched judge relied on compacted-session summaries for seven criteria.
patchpad-editor | gpt-5.6-sol (prior run) | 0.6842 | 1 | 595 | 6060 | Superseded score: the QC found multiple unsupported passes. The new evidence gate rejects the archived run's missing-marker reasoning.

## PatchPad 1.3
ID | Type | Sev | Status | Origin | Area | What the rework did / what is wrong | Action needed | Owner | Track
PP-01 | Prior | P0 | FIXED |  | Grading correctness | The prior batched judge awarded criteria without performing their exact named probes. | Confirm the next model run records zero evidence-gate false passes. |  | Closed
PP-02 | Prior | P0 | FIXED |  | Oracle validation | The prior Oracle used compacted context summaries for 7 of 20 criteria. | Run a fresh Oracle and require full score with no prior-session language. |  | Closed
PP-03 | Prior | P0 | FIXED |  | Graded but not stated | Contiguous typing, typed selection replacement, Replace All atomicity, and redo invalidation were graded but absent from the brief. | None. |  | Closed
PP-04 | Prior | P1 | FIXED |  | Judge protocol | The prior judge repaired content after a destructive API probe and still passed the criterion. | None. |  | Closed
PP-05 | Prior | P1 | FIXED |  | Auditability | The prior run retained only free-text criterion reasoning and no Claude/Playwright transcript. | Verify the next Harbor artifact contains non-empty transcript JSONL files. |  | Closed
PP-06 | Prior | P1 | FIXED |  | Rubric ordering | The pristine revision-1 seed check was not guaranteed to run before mutating criteria. | None. |  | Closed
PP-07 | Prior | P1 | FIXED |  | Over-strict rubric | The brief allowed Alt+Click or Ctrl/Cmd+Click while both criteria required Alt only. | None. |  | Closed
PP-08 | Prior | P2 | FIXED |  | Archive hygiene | A Windows launcher exposed a private relative Node toolchain path in shipped artifacts. | None. |  | Closed
PP-09 | Prior | P2 | FIXED |  | Stated but not graded | Restart idempotency and APP_MANIFEST completeness were mandatory but ungraded. | None. |  | Closed
PP-10 | Prior | P2 | FIXED |  | Result reporting | Unweighted passed/total counts appeared beside a weighted score without being named as criterion counts. | None. |  | Closed
PP-11 | Prior | P3 | FIXED |  | Harness robustness | A stale process could theoretically occupy PORT and satisfy health checks after the intended app failed to bind. | None. |  | Closed
PP-12 | Prior | P3 | FIXED |  | Budget calibration | The prior agent used about ten minutes of a three-hour allowance. | None. |  | Closed
PP-13 | Prior | P3 | FIXED |  | What is good | The prior report recorded reward-on-crash, secret hygiene, deterministic seed arithmetic, and tiered weights as strengths. | None. |  | Closed